## High level schedule
V3
2017
| Mar. | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Schedule V2
2017
| Mar. | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Phase 1:
Info collection
& reduce options
Phase 2
Option study with boundary & Narrow down to one direction
Phase 3
Work on detail definition & Spec drafting
Phase 4
Spec review and approval in Server WG and IC
Possible start of new
platform planning
Milestones
- Specification draft complete
- Mechnical profile defined and agreed in subgroup
- Baseboard- card connector and pinout defined and agreed in subgroup
- Adopted by at least one baseboard and one NIC
Milestones
- Setup and agree on 90/10 and 50/50 Boundary condition
- Narrow down to no more than 2x major implementation approaches
Milestones (status as of 7/5)
- Finish thermal simulaton of typical cases (50%?)
-> more analysis on ASIC@working and standby
- Agree on the result of simulation and feasiblity of NIC and system implementation (-> need more system engagement and input)
- Agree on to 1x implementation direction
- Identify potential enablers
- identify connector candidates
- Mechnical/packaging implementation
Milestones
- Specification passed server work group review
- Specification voted and approved by IC
Phase 1:
Info collection
& reduce options
Phase 2
Option study with boundary & Narrow down to one direction
Phase 3
Work on detail definition & Spec drafting
Phase 4
Spec review and approval in Server WG and IC
Possible start of new
platform planning
Milestones
- Specification draft complete
- Mechnical profile defined and agreed in subgroup
- Baseboard- card connector and pinout defined and agreed in subgroup
- Adopted by at least one baseboard and one NIC
Milestones
- Setup and agree on 90/10 and 50/50 Boundary condition
- Narrow down to no more than 2x major implementation approaches
Milestones
- Finish thermal simulaton of typical cases
- Agree on the result of simulation and feasiblity of NIC and system implementation
- Agree on to 1x implementation direction
- Identify potential enablers
Milestones
- Specification passed server work group review
- Specification voted and approved by IC

## Break down
| Phase 1 | 3/1/2017 - 4/14/2017
| Phase 2 | 4/17/2017 - 8/23/2017
| Phase 3 | 8/24/2017 - 10/1/2017
| Phase 4 | 10/1/2017 - 11/30/2017
Status | Phase | Date | Tasks | Notes
Close | Phase 1 | 3/1/2017 - 4/14/2017 | Design Boundary collection
Open | Phase 1 | 2017-04-19 | Share with community with survey result
Open | Phase 2 | 2017-04-19 | Propose, discuss, and agree on simulation methodology
Open | Phase 2 | 4/19 - 5/3 | Propose, discuss, and agree on simulation cases with different combination of boundaries from phase 1
Open | Phase 2 | 5/3 - 6/2 | Modeling and perform simulation cases on one major Mezz 3.0 design option with most consensus, while keep other options on the table
Open | Phase 2 | 6/5-6/21 | Discuss and agree on the simulation result | Not on track; to be updated
Open | Phase 2 | by 6/30 | Revisit remaining Mezz 3.0 design options and converge 1x major option | Not on track; to be updated
Open | Phase 2 | by 6/30 | Identify potential enablers | Not on track; to be updated
Open | Phase 3 | 7/5/2017 - 9/1/2017 | Detail to be provided | Not on track; to be updated
Open | Phase 4 | 9/4/2017 - 10/27/2017 | Detail to be provided | Not on track; to be updated
4/19/2017 - 2nd meeting of April
1st round review of WIP of study (target to provide snap shot of the status on 4/14)
Discussion to do course correction, and converge to 1x option if possible
5/3/2017 - 1st meeting of May
5/17/2017 - 2nd meeting of May
6/7/2017 - 1st meeting of June
6/21/2017 - 2nd meeting of June