## Readme
OCP Server Workgroup OCP NIC subgroup
Potential changes tracked in this spreadsheet is based on 0v72
http://www.opencompute.org/wiki/Server/Mezz

## Change tracker
ID | Category | Open Date | Status (Open/Discard/Push to Rev) | Revision | Key ppl | High level description of potential change | Impacts to NIC/System for potential change | Status / Action | 2018-04-25 | 2018-05-14 | 2018-05-21 | TN comments 20180526a
1 | General | 2018-04-04 | Discard | N/A | Paul @ HPE Thomas @ Intel | Hot plug related hardware features, to use a pre-charge pin to allow hot plug of a module with a low cost design (without HSC). | Circuit on both baseboard and NIC Golden finger design of NIC | 7/2 - No circuit change is made - Agree to discard this motion Added text@3.11 to clarify 6/7 Still under Email discussion; The proposed circuit needs more review. 5/14 - Major tradeoff: + Power capability will be reduced in this scheme + if the pre-charge resistor is replaced by other comp, it allows to get some capability back - Discussion +Pre-charge path is preferred to be on the left side of fuse +What is the purpose of the diodes? (Paul: do not know; to find out) +Fuse sizing is performed by NIC suppliers, no intend to include in specification. Fuse in this diagram(from HPE) is for reference only - Related to the pre-charge circuit: +In-rush is not specified in current spec; propose to define the expected result (e.g. No more than x A within Y us ) +Limiting factor 1: Server power delivery +Limiting factor 2: connector +Suggest to evaluate 2A (leverage from SFF-TA1009 ) as starting point from both NIC and Baseboard side; no more than 2A in any 5uS window (pre-charge can take longer than 5us) +Timing from pre-change to short pin contact (by-passing of pre-charge path). +Paul helps to find out “mechanical delay” range +Size of cap on card has a max range (1000uF) 4/25: Skipped as Paul@HPE is not there OPEN 4/18: WIP - Copy TN and Jia on the discussion on the electrical change |  | 5/14 - Major tradeoff: + Power capability will be reduced in this scheme + if the pre-charge resistor is replaced by other comp, it allows to get some capability back - Discussion +Pre-charge path is preferred to be on the left side of fuse +What is the purpose of the diodes? (Paul: do not know; to find out) +Fuse sizing is performed by NIC suppliers, no intend to include in specification. Fuse in this diagram(from HPE) is for reference only - Related to the pre-charge circuit: +In-rush is not specified in current spec; propose to define the expected result (e.g. No more than x A within Y us ) +Limiting factor 1: Server power delivery +Limiting factor 2: connector +Suggest to evaluate 2A (leverage from SFF-TA1009 ) as starting point from both NIC and Baseboard side; no more than 2A in any 5uS window (pre-charge can take longer than 5us) +Timing from pre-change to short pin contact (by-passing of pre-charge path). +Paul helps to find out “mechanical delay” range +Size of cap on card has a max range (1000uF) | XX | No action. HPe to drive with other baseboard vendors. This topic is moving very slowly and we are up agains the 0v80 release at the end of May'18.
2 | General | 2018-04-04 | Close | 0v80 | Thomas @ Intel | A few Leakage risk was identified RBT, Wake_N, BIF, Scan Chain; Edits are made into 0v80 to prevent leakage | Impact to circuit on both NIC and Baseboard. | 6/6 Agreed and reflected in 0v80 3.4.1 3.4.4 3.4.5 3.5.5 - RBT/BIF + isolation circuit at baseboard + isolator is enabled no earlier than AUX_PWR_EN assertion Wake#/ + isolation circuit at NIC + isolator is enabled by AUX_PWR_GOOD - Scan chain: + data out (baseboard to NIC) shall be drive to zero on baseboard before power enable. 5/21 - RBT: + isolation circuit at baseboard agreed by Intel/Broadcom/Cavium/Mellanox/FB/ Dell/HPE. + isolator is enabled by - Wake and BIF same as last discussion. Above plan is settled and okay to make change - Scan chain: + data out (baseboard to NIC) shall be drive to zero on baseboard before power enable. + racing condition between power enable and nic power okay; but NIC may need SLOT_ID1 before power on; Slot ID1 is needed when NIC is powering up and load FW. The leakage concern is hard to solve when SLOT ID is implemented on scan chain. Thinking about moving SLOT_ID1 back to edge pin. Further follow up needed. 5/14 - Move RBT isolation to the baseboard side ; Need more feedback from System ppl + Paul@HPE to find out HPE's platform take + Agree : Intel/Broadcom/Cavium/Mellanox/FB/ Dell + Thomas@Intel will start modify the diagram to reflect the proposal - Wake# is OD @ interface - same as existing standard(PCIe CEM, "Example WAKE# Circuit Design"). - BIF + reference implementation in 0v73_0511; Baseboard to handle BIF signal (either static or dynamic) in right timing to avoid leakage concern. - Scan chain + further investigation 4/25 Key takeaways - NIC suppliers have general concern around implementing isolation circuit on NIC due to relative smaller board space. Suggest to implement isolation circuit on system side for this reason. Want to collect system suppliers' feedback - Suggest to document requirement to the interface, instead of requirement of isolation circuit implementation. Isolation circuit can still be included in spec as implementation example (not requirement) 4/18 - RBT: 1) for use case there is more than 1x NIC in system; e.g.: one NIC shall handle RBT to certain state during ID mode, to allow host to access another NIC on RBT on this parallel bus. 2) concern with having HW overhead on all card implementation on a "corner case" 3) Leakage may still happen during ID mode when ASIC is not powered. - WAKE# : change to define expected behavior on GF, leave the implementation outside of specification TN 20180410 - Recommended approaches as written in 0v73: - RBT quickswitch for signals gated by AUX_PWR_EN - WAKE# - a FET gated by AUX_PWR_EN - BIF# pins - driven low by baseboard prior to AUX_PWR_EN. For static designs, logic '1' BIF pins are tied to AUX_PWR_EN. Logic '0' pins are directly connected to GND. |  | 5/14 - Move RBT isolation to the baseboard side ; Need more feedback from System ppl + Paul@HPE to find out HPE's platform take + Agree : Intel/Broadcom/Cavium/Mellanox/FB/ Dell (To confirm w/ Jon L) + Thomas@Intel will start modify the diagram to reflect the proposal - Wake# is OD @ interface - same as existing standard(PCIe CEM, "Example WAKE# Circuit Design"). - BIF + reference implementation in 0v73_0511; Baseboard to handle BIF signal (either static or dynamic) in right timing to avoid leakage concern. - Scan chain + further investigation | 5/21 - RBT: + isolation circuit at baseboard agreed by Intel/Broadcom/Cavium/Mellanox/FB/ Dell/HPE. + isolator is enabled bu - Wake and BIF same as last discussion. Above are settled - Scan chain: + data out (baseboard to NIC) shall be drive to zero on baseboard before power enable. + racing condition between power enable and nic power okay; but NIC may need SLOT_ID1 before power on; Slot ID1 is needed when NIC is powering up and load FW. The leakage concern is hard to solve when SLOT ID is implemented on scan chain. Thinking about moving SLOT_ID1 back to edge pin. Further follow up needed. | Closed? Just need community to respond on SLOT_ID1 definition: RBT, WAKE, BIF isolation done. SLOT_ID1 definition moved to pin location OCP_A6. Draft has been provided to the community to review change proposal.
3 | General | 2018-04-04 | Close |  | Hemal @ Broadcom | 1) Remove self-shutdown as a requirement to the NIC - Instead, change it to an optional feature. 2) Define the behavior when a NIC supports this feature | Impacts NIC implementation (from require to optional) Impacts system in terms of expectation to NIC | 11/20 Self shut-down edit is included in 0v85 push; close this item 11/6 Self shut-down is included in 0v84 candidate (need double check) 9/5 Broadcom plans to draft a revised section on self-shutdown by mid-Sept and send it out for review 9/4 No update in the past month. Not able to make into 0v83 7/31 Not able to push to 0v82 7/2 Not able to push to 0v81 Defer the push 6/18 Hemal is still working on it. shoot for End of June. Hemal plans to send Summary of change for quick discussion before writing it up. 6/6 Did not make to 0v80 Hemal is working on it 5/21 - Make feature optional (reflected in 0v73_0516a) - If an ASIC (or NIC) supports this feature, the feature of "self-shutdown" shall be able to turn on and off - When the "self-shutdown" is triggered on any component on NIC, the NIC is not expected to be function by system. - Hemal @ Broadcom to help draft this session (in 4.4) and define the behavior when supported. 4/25 Did not reach conclusion - follow up is needed. TN 20180410 - Text redlined. Recommend removing this requirement. 4/18 - TN: The thinking is to have a more graceful way to let system manage the shutting down - Level of warnings |  |  | 5/21 - Make feature optional (reflected in 0v73_0516a) - If an ASIC (or NIC) supports this feature, the feature of "self-shutdown" shall be able to turn on and off - When the "self-shutdown" is triggered on any component on NIC, the NIC is not expected to be function by system. - Hemal @ Broadcom to help draft this session (in 4.4) and define the behavior when supported. | Open. I pinged Hemal for an update on 5/25/2018. I haven't seen an updated proposal yet.
4 | General | 2018-04-04 | Close | 0v80 | Long @ Broadcom Thomas @ Intel Jia@FB | Update label requirement | Impacts the labeling on NIC side | 6/6 Refreshed in 0v80 with label example included 5/21 - QR code scan will return all MACs - Clarify the label example we plan to put in the spec is "Example", not Requirement - Hemal/Long has concern with the requirement being specific; Hemal and Long to review the draft and give feedback 5/14 - Label example (Intel/Broadcom/Mellanox/Cavium-TBD plan to generate examples ) - Jia to send out an email to request label example based on 0v73_0511a, for the group to review and combine to a label example to be included in spec. - Request 1: Dual port single host with 2x data MAC and 1x Management MAC - Request 2: Single Port Multi-host with 4x data MAC and 1x management MAC === Intel typically provide 1x base value, with # of MACs shown on the label. Mellanox typically explicitly show both data and management 5/2 - In discussion in ME working session - Long proposed updated Text for review TN 20180410 - Johnathanh Mai @ Intel says he'll take a look | X- very high level more detail to be covered in ME | 5/14 - Label example (Intel/Broadcom/Mellanox/Cavium-TBD plan to generate examples ) - Jia to send out an email to request label example based on 0v73_0511a, for the group to review and combine to a label example to be included in spec. - Request 1: Dual port single host with 2x data MAC and 1x Management MAC - Request 2: Single Port Multi-host with 4x data MAC and 1x management MAC === Intel typically provide 1x base value, with # of MACs shown on the label. Mellanox typically explicitly show both data and management | 5/21 - QR code scan will return all MACs with ?? In between? - Clarify the label example we plan to put in the spec is "Example", not Requirement - Hemal/Long has concern with the requirement being specific; want to review the draft and give feedback | I provided text updates 5/25/2018. This is also in the updated draft specification.
5 | General | 2018-04-04 | Close | 0v80 | Thomas @ Intel | Clean up of pinout table in section 3.4 / 3.5 | No impact to design; documentation improvement | 5/21 Close - included in 0v80 4/25 reviewed this change briefly; trending to close mainly a structure change TN 20180410 - Pin out table merged. Redlines shown for changes only. Text that was the same does not show tracked changes, but moves are noted. | Completed in 0v73 | Close? | close | Issue is closed.
6 | SI | 2018-04-04 | Open |  | SI workshop | SI work group Expected ~ Aug'18 - final contribution Draft in June'18 | Impacts SI margin and allocation of margin Impacts NIC and System SI planning | 9/5 0v83 has section 5.3 edited to include high level requirements and pointer to related PCI-SIG docs to follow. OCP foundation is helping to check with PCISIG and find out how to include Description of the OCP NIC 3.0 CLB and CBB test figure for use in the PCIe Architecture PHY Test specifications. The ask is brought to PCI-SIG with clarifications made. Expect to hear back in ~ 2 weeks after PCI-SIG gets a chance to discuss. 7/31 Jon@Dell is leading an ongoing discussion with OCP foundation and PCI-SIG to set a proper process for this workgroup to release the methodology and CLB & CBB fixture for PCIe Gen4 testing, from contributers to OCP, and from OCP to genreal public. The scope of discussion is the test platform and methodologies considered as non public common knowledge. 7/6 Some update about NC-SI over RBT routing is added in 5.1 of 0v81. This item shall remain open unitl other work around SI is reviewed and ported. 7/2 Samit @ FB: • SI working group will have an internal review on 7/3/2018 – for both SI requirement and validation strategy • Plan to share first draft with working group by mid-July for comments • Still on track to release first draft by end of August Thoams@Intel: 0v81 draft has the NC-SI recommendation added, and some high level overview of PCIe - more about PCIe to be added, likely in 0v90. Next step: call out the change and get feedback to include in 0v81 or not. 5/2 Clarified the timeline TN 20180410 - provided initial PCIe and RBT outline. SI Working Group to fill in | no plan to cover today to be covered in SI session later today |  | skip | Low attendance on the 5/23/2018 SI work group session or key stake holders. Meeting ajourned.
7 | Thermal | 2018-04-04 | Close |  | Yueming @ FB | Fill in the TBDs | No impact to design; documentation improvement | 9/5 Closed most of TBDs except the "tier definition" Close this item and merge the tier definition to item #9 based on the community call. 5/2 - some progress is made - Thermal WS is working on - Rob@ Dell sent a draft for review - may take 1-2 working session to finalize | no plan to cover today to be covered in thermal session next Wed |  | skip | I pinged Rob for an update 5/26/2018
8 | Thermal | 2018-04-04 | Close | 0v80 | Yueming @ FB | LFF thermal guidance | Impacts the thermal design in LFF | 6/6 included in 0v80 5/2 - included in Rob's draft - next step - review and agree on - may take 1-2 working session to finalize | no plan to cover today to be covered in thermal session next Wed |  | skip | I pinged Rob for an update 5/26/2018
9 | Thermal | 2018-04-04 | Open |  | Yueming @ FB | Perform Testing in fixture to confirm Tier definition reserved in the FRU EEPROM | Impacts the thermal design in SFF and LFF | 9/5: 1. Tier definition will be obtained after testing in fixture 2. After that, definition will be mapped to EEPROM requirement 5/2 - timeline TBD; hope to make into 0.9 or 1.0 but gated by card sample | no plan to cover today to be covered in thermal session next Wed |  | skip | ???
10 | ME | 2018-04-04 | Close | 0v80 | Dell-EMC Joshua @ FB | SFF NIC with internal lock - to prevent operator error | Small PCB change at NIC side with the goal of keeping PCB size same, using keep out area | 6/7 Included in 0v80 5/2 - good general alignment; will try to agree on changes in 1-2 working sessions 4/25 - Call for response on having the notch on NIC PCB - Long@BRCM: prefer to have one outline to manage | no plan to cover today to be covered in ME session next Wed |  | skip | The mechanical drawings show this feature and will be incorporated into the 0v80 specification. Johnathanh Mai is providing the text update and Thomas will incorporate it into the live draft for 0v80.
11 | ME | 2018-04-04 | Close | 0v80 | Joshua @ FB | LFF ejector layout - from dual ejector to single ejector as a ME improvement | Impact the ejector and bracket design Does not impact the PCB design | 6/7 Included in 0v80 5/2 - good general alignment; will try to agree on changes in 1-2 working sessions | no plan to cover today to be covered in ME session next Wed |  | skip | The mechanical drawings show this feature and will be incorporated into the 0v80 specification. Johnathanh Mai is providing the text update and Thomas will incorporate it into the live draft for 0v80.
12 | ME | 2018-04-04 | Close | 0v80 | Johnathanh @ Intel | Fill in the TBDs and clean up; ME assembly drawing improvement (add perforation in 2D, etc) | Does not impact implementation | 6/7 Included in 0v80 5/2 - good general alignment; will try to agree on changes in 1-2 working sessions | no plan to cover today to be covered in ME session next Wed |  | 5/21 - possible thumb screw change to be settled | The mechanical drawings show this feature and will be incorporated into the 0v80 specification. Johnathanh Mai is providing the text update and Thomas will incorporate it into the live draft for 0v80.
13 | General | 2018-04-04 | Close | 0v80 | Thomas @ Intel | move LED from ME to electrical; confirm labeling vs. marking | Reformatting only | TN 20180410 - Moved into the electrical section (Section 3.8 in 0v73 20180410c) 4/25 Ported, Discussed and closed | X |  | close | Issue is closed.
14 | General | 2018-04-04 | Close | 0v80 | Thomas @ Intel Warren @ Lenovo | Line side connector plating; define min insertion cycles and min plating thickness. | Impacts NIC connector selection | 6/6 Agreed and change is reflected in 0v80 5/21 Tony Sass @ Lenovo presentation Follow up with TE/FCI for the requirement proposed below: For 5-7year field life, specify: – SFPs 30 u” Au min. – RJ45s 50 u” Au min. OR Supplier to publish test results per EIA 364-1000 with these parameters - 200 durability cycles (20 preconditioning) - 7 year field life (MFG testing required) - Maximum change in LLCR for any test sequence is 10 milliohms 5/2 - Warren@Lenovo may put together a tech presentation and suggested edit of spec - David @ TE - SFF is specifying mating cycle; sometime the edge card is the limitation. ; Zhineng@Amphenol: prefer to use Cycle 4/25 - propose to specify both cycle and thickness - next step is to get TE/Amphenol input ======== - Broadcom : specify cycle , asked by sys, request to connector supplier - Cavium : specify both - Netronome: specify cycle to connector suppliers - Mellanox : TBD - Lenovo: ask for thickness as current practice - Intel: mixed | X | XX | 5/21 Tony Sass @ Lenovo presentation | This is an open topic and I'm looking for the working group to provide recommended text.
15 | General | 2018-04-04 | Close | N/A | Arash / Michael @ TE | Confirm the conformance to SFF-TA1002 SI requirement of all defined connectors. Lower SI risk until sample is ready | Does not impact implementation. | 4/25: Confirmed and closed Arash-TE 4/10 - Up to 32 gbps NRZ was evaluated . The requirements up to 112gbps PAM4 will need further evaluation. | close? |  | Close | Issue is closed.
16 | General | 2018-04-25 | Close | 0v80 | Thomas @ Intel | Add SLOT_ID1 to allow 2 bits to increase slot ID combinations from 2 slot (1bit) to 4 slot(2bits) | Impact both Baseboard and NIC | 6/6 Agreed and change is reflected in 0v80 5/21 - in scan chain now, but with leakage risk (refer to item 2) - decidion to be made between scan chain and physical pin 5/2 - in active discussion |  | X | 5/21 - in scan chain, but with leakage risk (refer to item 2) - decidion to be made between scan chain and physical pin | I provided text updates 5/25/2018. This is also in the updated draft specification. The SLOT_ID1 function has been moved to a physical pin - OCP_A6 (this was GND)
17 | General | 2018-05-07 | Close | 0v81 | Jia @ FB / Yuval @ Mellanox / Thoams @ Intel / Yan @ Tencent | UART on interface Want to bring this up for a community member. 1) is there value to have console interface from SOC/device on OCP NIC? This is typically done on UART 2) if so, is there a way to support it through the interface already defined; and if not, shall we consider adding this. | Impact baseboard / NIC | 7/6 included in 0v81 7/2 Discussion on Dell-EMC's proposal: - Adding USB2.0_p/n on Primary A68/69 - Adding UART_Tx/rx on Secondary A68/A69 - Need to watch for the SI due to A69 is next to Power_brake_n - Not using up all the RFU pins on Primary - Define as an optional feature. - Prioritize USB2.0 on Primary due to it has a path to use support both USB and UART. - Bridge for Reference: CP210x USB to UART Bridge VCP Drivers; FTDI has a 3x3 parts Question1: What is the primary use case of additional sideband (UART and/or USB) on SFF? Intel: - USB give more option(more than UART, examples.. FPGA and native USB ports), and flexibility; it is preferred regardless of form factor size. Smart-NIC on SFF is an interesting use case. - If we are not that sure what is the primary use case of sideband, we shall pick the one more flexible (USB) to leave some pin unused. Mellanox: Suggest to swap the UART to primary connector due to most use case for sideband is UART to avoid NIC carrying the USB-UART bridge overhead in limited board space. Idea: - Have both options on SFF on RFU1,2,3,4 on primary pin. - Shift a predefined one(say UART) to secondary connector on LFF. Smart-NIC on SFF is an interesting use case. - Checking HW guys on the size of bridge fitting on SFF NIC with native UART Broadcom: - No need for USB on SFF; For SFF, UART possible useful in future, but not today. Cavium: check internal Dell: - Wants to avoid muxing things on baseboard. - There are small bridge 3x3 ~ 4x4mm2 and 0.75?? mm tall, fits on the back side - For NIC requires either USB and UART, the cost of bridge is relative low Lenovo: - Prefers dedicate pins, i.e. avoid muxing 2x interfaces on same pins HPE: - Main use case is SFF, looking for max flexibility on Primary connector, and prefers USB - Avoid using up all 4x RFU pins on Primary connector to leave some future flexibility (as HPE primarily using SFF) Next step1: - 3x NIC suppliers (Mellanox, Broadcom, and Cavium) to check internal about the proposal from Dell-EMC and use email to reply by Noon Tue 7/3, in order to get the change out in 0v81. Question 2: Do we need 5V at connector for USB2.0 defined at interface? Next step 2: check Voltage to bridge and USB+/- signal, and see if there is issue with having only 2x wires for USB2.0 implementation. 6/18 Summary of status: 0v80 does not have UART defined. Thomas@Intel plans to propose an optional implementation. on high level, the overhead of circuit is on NIC side for Smart NIC needs UART. 5/21 - pin re-map is implemented in 0516a version (done) - clarify it is an optional (done) - isolation is currently defined on baseboard side, same as RBT (to confirm with community) - we need to make sure we only have 2x RFU pins left after this change (to confirm with community) + the risk is that someone may already have a plan to use these 2x pins (or 4pins) for other function - Change QuickSwitch to some general name Jia to send out an email with the goal of 1. raise awareness of the usage of the 2x RFU pins of last 4x RFU pins, and ask if anyone has feature counting on them. 2. confirm the isolation on system side is okay with NIC and sys suppliers 5/14 - Use 3.3V_Aux - Isolation during ID stage needed, implement on baseboard side - Detail UART isolation/ termination requirements - It is proposed as an optional feature for NIC - only applicable for NIC has UART interface, typically used as console of an SOC / Processor - Speed TBD , likley use typical console default speed - Plan to use RFU - Propose B69 and A70 pn Primary Connector (B69 RFU1 UART_TX, Baseboard->NIC ; A70 RFU4 UART_RX, NIC->Baseboard) - Add field in FRU EEPROM for UART support capability ===== |  | 5/14 - Use 3.3V_Aux - Isolation during ID stage needed, implement on baseboard side - Detail UART isolation/ termination requirements - It is proposed as an optional feature for NIC - only applicable for NIC has UART interface, typically used as console of an SOC / Processor - Speed TBD , likley use typical console default speed - Plan to use RFU - Propose B69 and A70 pn Primary Connector (B69 RFU1 UART_TX, Baseboard->NIC ; A70 RFU4 UART_RX, NIC->Baseboard) - Add field in FRU EEPROM for UART support capability ===== | 5/21 - pin re-map is implemented in 0516a version - clarify it is an optional (done) - isolation is currently defined on baseboard side, same as RBT - HPE (Mike/Paul to answer) - we need to make sure we only have 2x RFU pins left after this change - the risk is that someone may already have a plan to use these 2x pins (or 4pins) for other function - Change QuickSwitch to some general name Jia to send out an email with the goal of 1. raise the awareness of the usage of the 2 RFU pins of last 4 RFU pins, and ask if anyone has feature counting on them. 2. confirm the isolation on system side is okay with NIC and sys suppliers | The UART seems to be accepted by the NIC suppliers. This is drafted in the latest specification.
18 | General / Thermal | 2018-06-07 | Close |  | Massey, Carl @ HPE | Propose to reduce the NIC ASIC(Not the whole adaptor) requirement to report temperature from 8w to 5W (or 3W if possible) | Impact NIC | 11/20 Close with 0v85 push. 11/6 reflected in 0v84 RC 9/5 Carl@HPE: Suggest to move forward with change the limit from 8W to 5W. Paul@Intel: We do have one 10G part in the range of 5W-8W that doesn't support temp reporting. going forward, all parts >= 5W will support temperature reporting. Next step: change spec to greater or equal to 5W, requires temperature reporting. The Intel legacy part - may require a work around. 9/4 No update or active discussion. Suggest to close for now as this does not gate implementation 7/31 - No active discussion on email - Defer the decision. not making into 0v82 7/2 - No active discussion on email - Defer the decision. not making into 0v81. 6/18 Yuval @ Mellanox : Mellanox does not have problem Paul @ Intel: there is legacy product with TDP between 5-8W does not support thermal reporting. Hemal @ Broadcom: Broadcom does not have problem with either 3W or 5W as threshold - plan to do more discussion on email thread
19 | General | 2018-06-15 | Close |  | Thomas @ Intel Jia @FB Zhineng@Amphenol | PCIe Gen4 CEM specifics AC match termination on aux pins where double gnd pattern is broken in PCIe CEM connector and causing mismatched impedance within PCIe diff pairs. Reference: PCI Express Card Electromechanical Specification Revision 4.0, Version 0.7 Draft (Clean) - section 9.2.6 This may or may not apply to the SFF-TA1002 connector, but want to bring it up for awareness and discussion. | Potentially Impacts NIC-baseboard interface pin definition and NIC implementation. | 9/5 Close after community meeting 9/4 Amphenol shared the data to contributors on 8/11. No concern is raised so far. Suggest to close. 7/31 FB reviewed the data and do not see risk with current implementation of spec, as there is no double GND pattern to start with, and the difference on SE being open/short/terminated is trivial. checking with Amphenol if data can be shared broadly as so far only Intel and FB got this data. 7/6 AFCI provided some data showing low impact to SI by left misc pins open/short/termination; under review of that data. 6/18 Mike@Cavium: a foot print issue for CEM T/H design, do not think it is applicable to OCP NIC 3.0. Zhineng Fan@Amphenol: seems a foot print issue for CEM T/H design.will take a look and comment. |  |  |  |  | X
20 | ME | 2018-06-18 | Open |  | Samir @ TE Joshua @ FB | A coming SFF-TA-1002 connector key size change on baseboard side, only apply to straddle mount style, for fool proofing of installing a connector 180 degrees to a baseboard. | Impacts Baseboard cut off for Straddle Mount only Old Baseboard design is only able to take old connector New baseboard design is able to take both old and new connector | 9/5 David @TE : - Update is in Draft, together with other updates - current version in public is SFF-TA-1002 Rev1.1 - working draft is Rev1.1.2 Keep open until the draft with change is finalized and published. 9/4 The update is not in public yet. Checking with spec owner for confirmation 8/1 The key width adjustment is moving forward. The draft is being edited. There is a target for this to be reviewed in SFF on Friday (8/3) and after this point would be made public to begin the spec review process. Plan to follow up accordingly 7/31 The latest pub version on SNIA.org is still rev 1.1 Checking with SFF-TA1002 Point of Contact for update. 7/2 Not put into 0v81, wait for the SFF-TA1002 Rev 2.0 being released mid-July 6/18 David @ TE Straddle mount only, and host side only increase the rib of the key, to prevent plugging a module up-side-down. David @ TE will help to send the change slide to the community. Make sure the System suppliers are aware of it. Jia @FB to check with John N @ HPE for SFF-TA-1002 schedule. |  |  |  |  | X
21 | General | 2018-06-18 | Close |  | Hemal @ Broadcom | PLDM over RBT is not supported in NC-SI 1.1 PLDM over RBT is supported starting NC-SI 1.2 NC-SI 1.2 draft plan to be published to Public in Q3'18 NC-SI 1.2 formal release to public time: TBD | Documentation and readability | 11/20 Close with 0v85 push. 11/6 remove the "1.2" in body; call out ": This capability is planned to be included in revision 1.2 of the DSP0222 NC-SI specification." Changes are made in 0v84 RC 9/5 Regarding NC-SI 1.2 spec, there is a tentitive plan to in PMCI WG of the DMTF to get a work-in-progress draft out in Sept/Oct time-frame. The final NC-SI 1.2 standard is planned to be published in Q4 2018 but it may take Q1 2019. For OCP NIC 3.0 spec, it may be sufficient to reference NC-SI 1.2 if there is public work-in-progress draft is available. - propose not to make change for now. 9/4 No update. Not able to push to 0v83 7/31 Not able to push to 0v82 7/6 Not in 0v81; defer the push 7/2: Thomas: Not in the 0v81 draft yet. Hope to take change prior to EOD Tuesday for 0v81 push. Hemal: will give it a try (no commit) 6/18: After discussion, plan to call out NC-SI PLDM over RBT shall follows NC-SI 1.2 WIP. Hemal plans to modify based on 0v80 and send back to Thomas for merging
22 | ME | 2018-07-02 | Open |  | Roy@ Mellanox Joshua@FB | Mellanox reported a difficulty with LED implementation on 4xSFP+ case |  | 9/5 On going discussion - plan to work on in the week of 9/10 ME workshop 7/31 under disucssion
23 | General | 2018-05-25 | Open |  | Yuval@Mellanox Thomas@Intel Jia@FB | Provision 1 x32 config in LFF BIF encoding |  | 9/5 TN@Intel : 2 x16 is a valid use caes. Okay to privision x32, but not aware of any host would support x32. Next step: follow up with Yuval before close 9/4 Suggest to close as there is no active discussion, and does not gate implementation of all current use cases 7/31 Not in active discussion 7/6 - Added from a missing email thread for tracking - 0v81 has x32 in table 5 ofr card definition - "OCP 3.0 Pinout 0v81_20180705a_TN" does not have x32 in BIF table yet.
24 | General | 2018-07-12 | Close | 0v82 | Yuval@Mellanox | PCIe CEM defines PERST# to be held low until after the root-complex starts the link activation OCP NIC 3.0 0v81 requires PERST shall be pulled high to +3.3V_EDGE on the baseboard | Error correction | 9/4 Close Change to: "PERST# shall be asserted low on the baseboard until the platform is ready to deassert reset. " 7/31 Corrected in 0v82 draft "PERST# shall be pulled low to ground on the baseboard. " 7/12 It is a error in in 0v81 and earlier. Plan to correct in 0v82 to pull down to GND on the baseboard to prevent cards from coming out of reset until the host is ready to enumerate devices
25 | General | 2018-07-12 | Close | 0v82 | Thomas@Intel | The 4 x4 Bifurcation diagram and text in Section 3.5.5.3 incorrectly defined the BIF[2:0] value as ‘0b010’ (single host, four sockets). This has been updated to a value of BIF[2:0]=0b110 (as a four host, 1 socket per host) example. The figure in Section 3.5.5.4 has BIF[2:0]=don’t care as the example is four discrete silicon devices. | Error correction | 9/4 Close 7/12 corrected in 0v82 draft
26 | General | 2018-07-12 | Close | 0v82 | Thomas@Intel | A more uniform card form factor terminology has been implemented in the spec. We should be calling these as SFF and LFF. In 0v81 and earlier, the card was called out as “small card” and “large card” | Documentation Improvement | 9/4 Close 7/12 improved in 0v82 draft
27 | General | 2018-07-31 | Close | 0v82 | Yuval @ Mellanox Thomas@Intel | Figure 88 has a typo in diagram 0b0011 is expected, while the resistor strapping shows 0b1100 | Error correction | 9/4 corrected in 0v82 and close
28 | Thermal | 2018-07-31 | Open | 0v85 | Jon / Rob @ Dell Yueming@FB | SFF Thermal Test Fixture final design files this week |  | 11/20 Board file is posted "OCP_NIC_3.0_thermal_TestFixture_BoardFiles_20181031" Double check if there is plan to post sch before closing. 9/5 The 3D CAD of fixture is valid (the 6/4 version) Dell is working on internal review process, with the goal of releaseing the PCB design as well (for power delivery, etc.) 9/4 Checking in with thermal teams 7/31 expect to release a final design file for SFF thermal test fixture later this week after some clean up work.
29 | ME | 2018-09-05 | Open |  | Joshua@FB | General ME improvement work related to CAD, BOM, Inspection criteria |  | 9/5 Plan to work them in ME work shop in the week of 9/10
30 | General | 2018-10-31 | Close | 0v85 | Thomas @ Intel | Refresh short-long pin from 0v84, and align with SFF-TA-1002/1009 | Impact NIC GF design Not functional critical for non-hot plug application Suggest to phase in at next NIC respin for NIC intended to support hot plug | 11/20 Close with 0v85 push 11/2 Trending on using LONG pins for Ground, and SHORT pins for everything else (power, single ended and differential signals). We’ll have better alignment with both the SFF-TA-1002 and SFF-TA-1009 specifications. Plan to be added into next rev For cards in-flight, this may result in a board spin, but this is our opportunity to make changes prior to the next release milestone.
31 | SI | 2018-10-31 | Open |  | Samit @ FB | OCP-NIC Gen4 card loss budget from 8dB (the loss budget for standard PCIe Gen4 AIC) to 6dB, due to its smaller size
|  | Open | 8
|  | Discard | 1
|  | Close | 22