## Readme
OCP Server Workgroup OCP NIC subgroup
Potential changes tracked in this spreadsheet is based on 0v72
http://www.opencompute.org/wiki/Server/Mezz

## Change tracker
ID | Category | Open Date | Status (Open/Discard/Push to Rev) | Revision | Key ppl | High level description of potential change | Impacts to NIC/System for potential change | Status / Action | 2018-04-25
1 | General | 2018-04-04 | Open |  | Paul @ HPE Thomas @ Intel | Hot plug related hardware features | Circuit on both baseboard and NIC Golden finger design of NIC | OPEN 4/18: WIP - Copy TN and Jia on the discussion on the electrical change 4/25: Skipped as Paul@HPE is not there
2 | General | 2018-04-04 | Open |  | Thomas @ Intel | Leakage current mitigation in RBT, Wake_N, BIF | Impact to circuit on NIC May impact NC-SI Signal timing as well | TN 20180410 - Recommended approaches as written in 0v73: - RBT quickswitch for signals gated by AUX_PWR_EN - WAKE# - a FET gated by AUX_PWR_EN - BIF# pins - driven low by baseboard prior to AUX_PWR_EN. For static designs, logic '1' BIF pins are tied to AUX_PWR_EN. Logic '0' pins are directly connected to GND. 4/18 - RBT: 1) for use case there is more than 1x NIC in system; e.g.: one NIC shall handle RBT to certain state during ID mode, to allow host to access another NIC on RBT on this parallel bus. 2) concern with having HW overhead on all card implementation on a "corner case" 3) Leakage may still happen during ID mode when ASIC is not powered. - WAKE# : change to define expected behavior on GF, leave the implementation outside of specification 4/25 Key takeaways - NIC suppliers have general concern around implementing isolation circuit on NIC due to relative smaller board space. Suggest to implement isolation circuit on system side for this reason. Want to collect system suppliers' feedback - Suggest to document requirement to the interface, instead of requirement of isolation circuit implementation. Isolation circuit can still be included in spec as implementation example (not requirement)
3 | General | 2018-04-04 | Open |  | Paul/Thomas @ Intel | Remove self-shutdown as a requirement to the NIC Investigate alternative approach | Impacts NIC implementation May impact system implementation if new mechanism requires system change | TN 20180410 - Text redlined. Recommend removing this requirement. 4/18 - TN: The thinking is to have a more graceful way to let system manage the shutting down - Level of warnings 4/25 Did not reach conclusion - follow up is needed.
4 | General | 2018-04-04 | Open |  | Long @ Broadcom Thomas @ Intel Jia@FB | Update label requirement | Impacts the labeling on NIC side | TN 20180410 - Johnathanh Mai @ Intel says he'll take a look | X- very high level more detail to be covered in ME
5 | General | 2018-04-04 | Open |  | Thomas @ Intel | Clean up of pinout table in section 3.4 / 3.5 | No impact to design; documentation improvement | TN 20180410 - Pin out table merged. Redlines shown for changes only. Text that was the same does not show tracked changes, but moves are noted. 4/25 reviewed this change briefly; trending to close | Completed in 0v73
6 | SI | 2018-04-04 | Open |  | SI workshop | SI work group Expected ~ Aug'18 | Impacts SI margin and allocation of margin Impacts NIC and System SI planning | TN 20180410 - provided initial PCIe and RBT outline. SI Working Group to fill in | no plan to cover today to be covered in SI session later today
7 | Thermal | 2018-04-04 | Open |  | Yueming @ FB | Fill in the TBDs | No impact to design; documentation improvement |  | no plan to cover today to be covered in thermal session next Wed
8 | Thermal | 2018-04-04 | Open |  | Yueming @ FB | LFF thermal guidance | Impacts the thermal design in LFF |  | no plan to cover today to be covered in thermal session next Wed
9 | Thermal | 2018-04-04 | Open |  | Yueming @ FB | Perform Testing in fixture to confirm Tier definition reserved in the FRU EEPROM | Impacts the thermal design in SFF and LFF |  | no plan to cover today to be covered in thermal session next Wed
10 | ME | 2018-04-04 | Open |  | Dell-EMC Joshua @ FB | SFF NIC with internal lock - to prevent operator error | Small PCB change at NIC side with the goal of keeping PCB size same, using keep out area | 4/25 - Call for response on having the notch on NIC PCB - Long@BRCM: prefer to have one outline to manage | no plan to cover today to be covered in ME session next Wed
11 | ME | 2018-04-04 | Open |  | Joshua @ FB | LFF ejector layout - from dual ejector to single ejector as a ME improvement | Impact the ejector and bracket design Does not impact the PCB design |  | no plan to cover today to be covered in ME session next Wed
12 | ME | 2018-04-04 | Open |  | Johnathanh @ Intel | Fill in the TBDs and clean up; ME assembly drawing improvement (add perforation in 2D, etc) | Does not impact implementation |  | no plan to cover today to be covered in ME session next Wed
13 | General | 2018-04-04 | Close |  | Thomas @ Intel | move LED from ME to electrical; confirm labeling vs. marking | Reformatting only | TN 20180410 - Moved into the electrical section (Section 3.8 in 0v73 20180410c) 4/25 Ported, Discussed and closed | X
14 | General | 2018-04-04 | Open |  | Thomas @ Intel Warren @ Lenovo | Line side connector plating; define min insertion cycles vs. min plating thickness. May refer to defined standard, which defines min - cycles. Prefer to use existing spec if available | Impacts NIC connector selection | 4/25 - propose to specify both cycle and thickness - next step is to get TE/Amphenol input ======== - Broadcom : specify cycle , asked by sys, request to connector supplier - Cavium : specify both - Netronome: specify cycle to connector suppliers - Mellanox : TBD - Lenovo: ask for thickness as current practice - Intel: mixed | X
15 | General | 2018-04-04 | Close |  | Arash / Michael @ TE | Confirm the conformance to SFF-TA1002 SI requirement of all defined connectors. Lower SI risk until sample is ready | Does not impact implementation. | Arash-TE 4/10 - Up to 32 gbps NRZ was evaluated . The requirements up to 112gbps PAM4 will need further evaluation. 4/25: Confirmed and closed | close?