## 0v99
OCP NIC 3.0 Review Tracker
File: | OCP_NIC_3.0_d0v99_20191214a_TN.docx
Comment ID# | Date | Commenter, Company | Affected Section(s) | Comment | Disposition | Status
1 | 2019-12-06 | Josh Held, Facebook | 2.x | Mechanical drawing change comments. Refer to e-mail chain for visuals. Text captured here: - Figure 25 detail B - Can we just drop the .002 entirely? That is comically small. It makes clarity of this view very difficult. - Figure 43 - I don’t think 110.01 should be reference, this is critical to function. I would hope we can get to +/-.3, we do have one less hole clearance but some clearance latch to press-fit hardware. Albeit hard to measure. What do you think? This is for SFF and LFF latch. - Figure 48 - The SFF internal lock variant side view CTF view has +/-.41 should be consistent with the others. - Figure 56 - LFF variant side view CTF view has +/-.42 should be consistent with the others. | Mechanical drawing updates received for the following Figures: 25, 41, 44, 47, 48, 51, 52, 55, 56 and 59. Some changes were cascaded by comments from initial figure list at left. Changes implemented in 20191209b and later. | Out for review
2 | 2019-12-06 | Warren Bailey, Lenovo | 4.10.3 | I have a concern about the value of the OCP NIC 3.0 FRU OEM Record Version defined for spec 0.90 revision compliance. There have been several adapters made based on spec 0.86 and later which already use the value of ‘01’ in this field. If it makes a difference whether the FRU record follows the .86 version or the 0.9 version then we cannot define the 0.9 value to be the same as the value already used by the predecessor designs. It would be better to start 0.9 with a value like ’02’ which has not been already used. As written today the spec allows no value that pre-0.9 adapters could use that is valid (all are reserved). | I walked through the concern with Warren and we discovered no conflicts with changes made between 0v86 and 0v90. 0v90 changed offsets 17-23 from Reserved to defined fields. The value 0xFF remains a reserved value (per 0v86). Warren agreed and this item is closed. | Closed
3 | 2019-12-08 | Warren Bailey, Lenovo | 4.10.3 | Maybe it would be better to use a designation of ‘not defined’ for FF in offsets 17:30 instead of ‘Reserved’. Usually in a spec that defines some but not all bit combinations of a field, ‘reserved’ means don’t use these values (this is how bits 6 and 7 are defined in offset 17 for example). Spec 0.86 explicitly tells people to use FF for offsets 17:30. ‘Not defined’ or some similar label might be better than ‘reserved’. Offsets 19 and 20 follow this train of thought because they use the term “unknown” for FF instead of ‘reserved’. It’s just a nit though. | Agreed. Proposal implemented in 20191208a and later. This changes the value definition "0xFF - Reserved" to "0xFF - Unknown" | Out for review
4 | 2019-12-08 | Thomas Ng, Intel | 4.10.3 | Offset 15 and 16 of the OEM record do not define values for "reserved" or "unknown" states. I suggest adding the following for completeness: Offset 15 - 0x02 – 0xFE – Reserved for future use 0xFF – Unknown Offset 16 - 0x04 – 0xFE – Reserved for future use 0xFF – Unknown | Implemented as suggested. Proposal implemented in 20191208a and later. | Out for review
5 | 2019-12-06 | Long Nguyen, Broadcom | 3.7.2 | There is no consistent method of measurement the LED brightness that I know of and so the requirement of defining an mcd range [12 to 18 mcd] is questionable unless the spec define a method of measurements. I would suggest to leave this out OR add some verbiage to clarify this requirement further. | 20191211 - Long @ Broadcom - recommends removing luminous intensity requirements of 12-18 mcd for both indicators. 20191213 - Alan Kyle @ Dell - recommends leaving it as-is and deferring the methodology definition for a post 1.0 fix. 20191213 - April Fisher @ Intel - recommends the following text: "For uniformity and usability across OCP NIC 3.0 products, green LEDs shall have their luminance measured in millicandelas (mcd) with a value between 10 mcd and 50 mcd. Amber LEDs shall have their luminance measured in millicandelas (mcd) with a value between 20 and 60 mcd. These measurements shall be taken directly at the faceplate. A recommended measurement methodology is a work-in-progress by the OCP NIC 3.0 Electrical Subgroup, and will be added in a future release." <== this text is currently drafted in. We can debate the values, but we should acknowledge the measurement methodlogy is a WIP for a future release. | Open
6 | 2019-12-08 | Mike Decesaris, Lenovo | 1.3 | I see the spec references draft 1.1, while release version 1.2 is available on the web. | The SFF-TA-1002 spec reference has been updated to R1.2, April 3rd, 2019. Text updated in 20191209a and later. | Closed
7 | 2019-12-08 | Mike Decesaris, Lenovo | Multiple instances through document | Looking toward future maintenance and realizing that [the connector] information (and more) comes from SFF-TA-1002, do we plan on keeping the OCP spec in lockstep with SFF-TA-1002, updating all related sections and releasing a new spec whenever a new version of SFF-TA-1002 is released? If not, should there be a statement stating that SFF-TA-1002 is the authoritative reference in sections where the subject matter is referenced entirely and not otherwise re-defined, further defined, restricted, etc? | Editor's note: From my perspective, the SFF-TA-1002 document should be the governing document as far as acceptable connectors. Duplicating this information in the OCP NIC 3.0 specification is redundant, but does provide some value for the reader. For future maintenance releases, we should try to remove the SFF-TA-1002 diagrams that are not absolutely required in our specification and point users to the TA-1002 document instead. Additionally, i agree that a statement along the lines of "The SFF-TA-1002 spec governs the acceptable connectors as long as they are form-fit-function compatible" We agreed that this is a Post 1.0 action. | Deferred for post 1.0
8 | 2019-12-10 | Thomas Ng, Intel | 2.3 | There is still a wave washer callout in the text below Figure 13. We moved to the clinch nut implementation a while ago. Item #8 and #11 – Wave washer and bushing are part of the ejector latch mechanism. | Per mechanical feedback: Remove callout #8, and #11 under Figure 13 as it is covered at the faceplate assembly; also remove callout #11 from the faceplate BOM (Table 9). | Closed
9 | 2019-12-12 | Roy Kauffman, Mellanox | 3.4.2 | We should recommend the pull up/down resistor values (in Figure 83). The spec does not currently define it. Suggest ~20mA of drive current. | Editor's note: Waiting on submitter confirmation. Suggested edit is to recommend the BIF pin pull up resistors as ~220 ohm (approximately 15 mA). A direct connection to ground is sufficient for a logic low. | Out for review
10 | 2019-12-13 | Mike Decesaris, Lenovo | 3.4.5 | While the clock rate is capped at 12.5 MHz in the spec, the pulse width of LD# and the delay between the edges of LD# and data valid are not defined. We have sampled several OCP adapters from different manufacturers and see that some manufacturers have used a CPLD for the scan chain instead of the 74LV165 used in the default implementation shown in the spec. ... While the baseboard vendor can control the LD# and CLK timings, the data valid is controlled by the adapter vendor. The large variance in timing makes it difficult to determine where our data sample strobe needs to be (rising or falling clock edge). We recommend that minimum pulse width and maximum delay values associated with data valid be added to the spec. | Editor's note: The proposed timings have been provided by Lenovo and shown below. This is a relaxed timing of the 74LV165 @ 3.3V for an operating temperature of 0 to +85 degC. This implementation is shown in version 20191214a of the spec. | Out for review
11
12
13
14
15
16
17
18
19
20