## 1v01
OCP NIC 3.0 Review Tracker
File: | OCP_NIC_3.0_d1v01_20200717a_TN.docx
Comment ID# | Date | Commenter, Company | Affected Section(s) | Comment | Disposition | Status
1 | 2019-12-06 | Long Nguyen, Broadcom | 3.7.2 | There is no consistent method of measurement the LED brightness that I know of and so the requirement of defining an mcd range [12 to 18 mcd] is questionable unless the spec define a method of measurements. I would suggest to leave this out OR add some verbiage to clarify this requirement further. | 20191211 - Long @ Broadcom - recommends removing luminous intensity requirements of 12-18 mcd for both indicators. 20191213 - Alan Kyle @ Dell - recommends leaving it as-is and deferring the methodology definition for a post 1.0 fix. 20191213 - April Fisher @ Intel - recommends the following text: "For uniformity and usability across OCP NIC 3.0 products, green LEDs shall have their luminance measured in millicandelas (mcd) with a value between 10 mcd and 50 mcd. Amber LEDs shall have their luminance measured in millicandelas (mcd) with a value between 20 and 60 mcd. These measurements shall be taken directly at the faceplate. A recommended measurement methodology is a work-in-progress by the OCP NIC 3.0 Electrical Subgroup, and will be added in a future release." | Deferred for post 1.0. MCD value range changed to "should be 12 to 18 mcd"; added text for methodology addition in a future release.
2 | 2019-12-08 | Mike Decesaris, Lenovo | Multiple instances through document | Looking toward future maintenance and realizing that [the connector] information (and more) comes from SFF-TA-1002, do we plan on keeping the OCP spec in lockstep with SFF-TA-1002, updating all related sections and releasing a new spec whenever a new version of SFF-TA-1002 is released? If not, should there be a statement stating that SFF-TA-1002 is the authoritative reference in sections where the subject matter is referenced entirely and not otherwise re-defined, further defined, restricted, etc? | Editor's note: From my perspective, the SFF-TA-1002 document should be the governing document as far as acceptable connectors. Duplicating this information in the OCP NIC 3.0 specification is redundant, but does provide some value for the reader. For future maintenance releases, we should try to remove the SFF-TA-1002 diagrams that are not absolutely required in our specification and point users to the TA-1002 document instead. Additionally, i agree that a statement along the lines of "The SFF-TA-1002 spec governs the acceptable connectors as long as they are form-fit-function compatible" We agreed that this is a Post 1.0 action. | Deferred for post 1.0
3 | 2019-12-12 | Roy Kauffman, Mellanox | 3.4.2 | We should recommend the pull up/down resistor values (in Figure 83). The spec does not currently define it. Suggest ~20mA of drive current. | Editor's note: Waiting on submitter confirmation. Mellanox: Suggested edit is to recommend the BIF pin pull up resistors as ~220 ohm (approximately 15 mA). A direct connection to ground is sufficient for a logic low. Dell: Dell is not in agreement with this change. This value of resistor and the associated current seems excessive without valid explanation. If PU/PD values are to be assigned we should use values that are aligned with High-Z inputs and not some constant current input. | Deferred for post 1.0
4 | 2020-07-09 | Thomas Ng, Intel | All | Merge comments from Scan Chain, Thermal Severity Level and PCIe compliance updates from May and June 2020 meetings | Completed. See change bars between 1.0 and d1.01 | Completed
5 | 2020-07-09 | John Stuewe, Dell | 3.9, Table 42 | I don’t think an ‘allowed’ leakage of up to 50ma makes any sense. If there is leakage the current will be coming from 3.3v and getting on 12v by mistake… and it can never go above 3.3v. Adding a current limit to leakage isn’t realistic. The original intent may have been to allow for components to ‘leak’ power FROM the 12v source but the text below is implying power leaked back INTO the 12v plane while it’s off. I think we should either A) state the leakage isn’t allowed when 12v is not present, or B) State that leakage is allowed when 12v is not present and that it’s the systems responsibility to either account for it or block it from getting back to the motherboard 12v, (which is off). Obviously option A is the clear choice if we had this in the original spec. The fact that we have hardware in the field may push us to Option B if we can’t verify the vast majority of current designs don’t have leakage. | I think option B " State that leakage is allowed when 12v is not present and that it’s the systems responsibility to either account for it or block it from getting back to the motherboard 12v, (which is off)” is likely the statement that we can make. I agree that since hardware is already in the field, we can’t mandate that +12V_EDGE is off during this time. I updated the text in 3.8.2 and 3.8.5 as follows: "Baseboards may disable +12V_EDGE in this power state. OCP NIC 3.0 cards are not intended to use +12V_EDGE in ID Mode, however leakage current may be present. It is the baseboard vendor’s responsibility to account for this or block it from feeding towards the motherboard. The max leakage is defined in Section 3.9. " The same text is used in programming mode section, but with "ID Mode" changed out to "Programming Mode"
5 | 2020-07-09 | Comment removed | Comment removed | Comment removed | Comment removed | Comment removed
6 | 2020-07-09 | John Stuewe, Dell | 3.4.6 | In table 32 the MAIN_PWR_EN description has the text “The MAIN_PWR_EN pin is driven by the baseboard and may only be asserted when AUX_PWR_EN is already asserted.” The next section describes programming mode where this isn’t true so we either need to amend this statement to account for programming mode or change it to state that AUX_PWR_EN must be asserted along with MAIN_PWR_EN in the MAIN(S0) state. | Clarified the first sentence as "The MAIN_PWR_EN pin is driven by the baseboard and may only be asserted when AUX_PWR_EN is already asserted for normal operation in the S0 power state." The change above should take care of the distinction between the normal power on flow and the following paragraph about Programming Mode operation.
7 | 2020-07-09 | John Stuewe, Dell |  | The timing and state diagrams don’t account for systems that doesn’t support AUX(S5). We’re assuming we can assert AUX_PWR_EN and MAIN_PWR_EN at the same time and go straight from ID MODE to MAIN(S0). Does anyone disagree? Should we update the state diagram in figure 105 to include this transition? | See comment #16 below that includes John and Damien's input
8 | 2020-07-09 | Damien Chong, Facebook |  | I did not see the updated text reflects what shown in figure 105 and table 42. The text says Baseboard may enable +12V_Edge in ID mode but figure and table asking it to be enabled. This would make our spec ambiguous. My feedback is we shall say the same thing in 3.8.2 text, figure 105 and table 42. Whether +12V_Edge is ON, OFF or OPTIONAL in ID_mode and programming mode. I think a quick poll and discussion with community is required. | I changed Table 42 "Available Card Functions Per Power state. Note 2 now reads "The +12V_EDGE rail may be disabled at this time…" This is in alignment with the current text from Section 3.8.2 and 3.8.5.
9 | 2020-07-09 | Damien Chong, Facebook |  | Secondly, there is a text update saying table 42 power is instantaneous power. If we intent to say it is instantaneous, I think we need to define the duration. If we don’t define the duration, it is best keep saying it is max power which could mean DC. Today we cannot dissipate 80W DC easily, but saying it is instantaneous without a duration is worse in my opinion. | I removed the word "instantaneous". Maybe that's the real point of contention is.
10 | 2020-07-10 | Thomas Ng, Intel |  | Remove "guaranteed" from TID timing parameter in Table 43 (power sequencing parameters) to align text with TSS, TAPL and TMPL timing descriptions. | Removed as noted.
11 | 2020-07-13 | John Stuewe, Dell |  | Your OCP_NIC_3.0_d1v01_20200710a_TN draft doesn’t include any clarifications on the items below. (TN: above, see 7/9 comments) In 3.8.2 & 3.8.5, I would add “if +12V_EDGE is present” before “The max leakage is defined in section 3.9” and possible add something like ‘If +12V_EDGE is not present, no voltage leakage from 3.3v is allowed, per section 3.4” | I changed the text in 3.8.2 and 3.8.5 to "If +12V_EDGE is present, the max leakage is defined in section 3.9." I think the second statement about "if +12V_EDGE is not present, no voltage leakage from 3.3V_EDGE is allowed" would be more difficult. April published some anonymized data of our cards in this scenario. There is some leakage on to +12V_EDGE from +3.3V_EDGE. Right now, the text says "it is the baseboard vendor's responsibility to account for this or block it from feeding towards the motherboard" -- not sure which one of the two options would be less painful for system and NIC implementors.
12 | 2020-07-13 | John Stuewe, Dell |  | In table 32 the MAIN_PWR_EN description has the text “The MAIN_PWR_EN pin is driven by the baseboard and may only be asserted when AUX_PWR_EN is already asserted.” The next section describes programming mode where this isn’t true so we either need to amend this statement to account for programming mode or change it to state that AUX_PWR_EN must be asserted along with MAIN_PWR_EN in the MAIN(S0) state. | Duplicate of #6, above. Closed. | Duplicate
13 | 2020-07-13 | John Stuewe, Dell |  | The timing and state diagrams don’t account for systems that doesn’t support AUX(S5). We’re assuming we can assert AUX_PWR_EN and MAIN_PWR_EN at the same time and go straight from ID MODE to MAIN(S0). Does anyone disagree? Should we update the state diagram in figure 105 to include this transition? | Duplicate of #7, above. As noted, see #16. | Duplicate
14 | 2020-07-13 | Damien Chong, Facebook |  | Hi Thomas, The OCP_NIC_3.0_d1v01_20200710a_TN.docx did not mitigate the concern I list in email on 7/9. >> Baseboards may enable +12V_EDGE in this power state. OCP NIC 3.0 cards are not intended to use +12V_EDGE in ID Mode, however leakage current may be present The first one is regarding flow chart and table asking +12V_EDGE to be ON during ID & Programming mode, the exception thru text in 3.8.2 should be Baseboards may enable disable +12V_EDGE in this power state. | Addressed with other comments above. Table 42, Note 2 now change to"Note 2: The +12V_EDGE rail is on may be disabled at this time, but the max permissible current draw is up to the ID Mode / Programming Mode current limit defined in Section 3.9.
15 | 2020-07-13 | Damien Chong, Facebook |  | >> The slot power values are the max supportable instantaneous power delivered to the card for each slot type Instantaneous power duration is not defined. If we want to update spec to mention instantaneous power, then we should define the duration. | Duplicate of #9, above | Duplicate
16 | 2020-07-13 | Damien Chong, Facebook |  | >> 2) The timing and state diagrams don’t account for systems that doesn’t support AUX(S5). We’re assuming we can assert AUX_PWR_EN and MAIN_PWR_EN at the same time and go straight from ID MODE to MAIN(S0). Does anyone disagree? Should we update the state diagram in figure 105 to include this transition? The spec is written that allow main power to be optional for NIC card that can operate within aux power budget. For system that doesn’t support aux mode, when transition to main mode, is it possible to design aux_pwr_en = 1 first? In case main_pwr_en = 1 first when ramp up both signal together, per state diagram it is an invalid transition to go from programming mode to main mode. For some NIC card, it might not be an issue. The more state transition we define, more validation needs to be done hence we have the basic one below. Is this acceptable to you? | There's an example power topology diagram that shows SVRs that are powered in the Aux domain and SVRs that are powered in the Main domain. Some card vendors could potentially have this condition. In that case, what happens when the two power domains power up at the same time? Is this allowed by the card vendor? Will it cause any issues? Does the Main Power SVRs depend on something coming up first in Aux Power mode? If the baseboard wants to assert AUX_PWR_EN and MAIN_PWR_EN at the same time, maybe it's an additional validation step required for that baseboard vendor only. ? | Open
17 | 2020-07-14 | Damien Chong, Facebook Tim Lambert, Dell |  | >> This is a Figure 105 nitpick on AUX mode stating S5, but with Hotplug support, ID, AUX and Main modes can exist while the system is in ACPI S0. Agree. I think we can remove “S5” and “S0” in figure 105. Anyone disagree? | I removed the text "S5" and "S0" from the lower two bubbles. | Completed
18
19
20