## Readme
OCP Server Workgroup OCP NIC subgroup
Potential changes tracked in this spreadsheet is based on 0v72
http://www.opencompute.org/wiki/Server/Mezz

## Change tracker
ID | Category | Open Date | Status (Open/Discard/Push to Rev) | Revision | Key ppl | High level description of potential change | Impacts to NIC/System for potential change | Status / Action
1 | General | 2018-04-04 | Open |  | Paul @ HPE Thomas @ Intel | Hot plug related hardware features | Circuit on both baseboard and NIC Golden finger design of NIC | OPEN
2 | General | 2018-04-04 | Open |  | Thomas @ Intel | Leakage current mitigation in RBT, Wake_N, BIF | Impact to circuit on NIC May impact NC-SI Signal timing as well | TN 20180410 - Recommended approaches as written in 0v73: - RBT quickswitch for signals gated by AUX_PWR_EN - WAKE# - a FET gated by AUX_PWR_EN - BIF# pins - driven low by baseboard prior to AUX_PWR_EN. For static designs, logic '1' BIF pins are tied to AUX_PWR_EN. Logic '0' pins are directly connected to GND.
3 | General | 2018-04-04 | Open |  | Paul/Thomas @ Intel | Remove self-shutdown as a requirement to the NIC Investigate alternative approach | Impacts NIC implementation May impact system implementation if new mechanism requires system change | TN 20180410 - Text redlined. Recommend removing this requirement.
4 | General | 2018-04-04 | Open |  | Long @ Broadcom Thomas @ Intel Jia@FB | Update label requirement | Impacts the labeling on NIC side | TN 20180410 - Johnathanh Mai @ Intel says he'll take a look
5 | General | 2018-04-04 | Open |  | Thomas @ Intel | Clean up of pinout table in section 3.4 / 3.5 | No impact to design; documentation improvement | TN 20180410 - Pin out table merged. Redlines shown for changes only. Text that was the same does not show tracked changes, but moves are noted.
6 | SI | 2018-04-04 | Open |  | SI workshop | SI work group Expected ~ Aug'18 | Impacts SI margin and allocation of margin Impacts NIC and System SI planning | TN 20180410 - provided initial PCIe and RBT outline. SI Working Group to fill in
7 | Thermal | 2018-04-04 | Open |  | Yueming @ FB | Fill in the TBDs | No impact to design; documentation improvement
8 | Thermal | 2018-04-04 | Open |  | Yueming @ FB | LFF thermal guidance | Impacts the thermal design in LFF
9 | Thermal | 2018-04-04 | Open |  | Yueming @ FB | Perform Testing in fixture to confirm Tier definition reserved in the FRU EEPROM | Impacts the thermal design in SFF and LFF
10 | ME | 2018-04-04 | Open |  | Dell-EMC Joshua @ FB | SFF NIC with internal lock - to prevent operator error | Small PCB change at NIC side with the goal of keeping PCB size same, using keep out area
11 | ME | 2018-04-04 | Open |  | Joshua @ FB | LFF ejector layout - from dual ejector to single ejector as a ME improvement | Impact the ejector and bracket design Does not impact the PCB design
12 | ME | 2018-04-04 | Open |  | Johnathanh @ Intel | Fill in the TBDs and clean up; ME assembly drawing improvement (add perforation in 2D, etc) | Does not impact implementation
13 | General | 2018-04-04 | Open |  | Thomas @ Intel | move LED from ME to electrical; confirm labeling vs. marking | Reformatting only | TN 20180410 - Moved into the electrical section (Section 3.8 in 0v73 20180410c)
14 | General | 2018-04-04 | Open |  | Thomas @ Intel Warren @ Lenovo | Line side connector plating; define min insertion cycles vs. min plating thickness. May refer to defined standard, which defines min - cycles. Prefer to use existing spec if available | Impacts NIC connector selection | OPEN
15 | General | 2018-04-04 | Open |  | Arash / Michael @ TE | Confirm the conformance to SFF-TA1002 SI requirement of all defined connectors. Lower SI risk until sample is ready | Does not impact implementation. | Arash-TE 4/10 - Up to 32 gbps NRZ was evaluated . The requirements up to 112gbps PAM4 will need further evaluation.